## Sheet1
| Feature/Requirement | Description | Test Steps/Acceptance Criteria | positive | negative | manual | automated | Overall Status | Assigned To
1 | Employee login | Employees should be able to login | link to feature file | (1.1) Scenario: Login With Correct Credentials | (1.3) Scenario: Login With Incorrect Credentials FAIL | 1.1 PASS, 1.2 PASS, 1.3 FAIL | 1.1 PASS, 1.2 FAIL, 1.3 NOT IMPLEMENTED | Incomplete | Adam Ranieri
(1.2 )Scenario: Login with forgot password
2 | Manager Dashboard View | Managers should be view high level details | link to feature file | (2.1) Scenario: Recent purchases shown | N/A | 2.1 PASS, 2.2 PASS | 2.1 PASS, 2.2 PASS | Completed | Donna Simpson
(2.2) Scenario: Pending Emails displayed